## Sheet1
Risk ID | Risk Type | Risk Description | Likelihood | Impact | Priority | Severity (L*I) | Mitigation Strategy | Contingency Plan
R1 | Operational Risk | Manual appointment scheduling leads to double bookings and patient delays | Medium | Medium | Mitigation Required | 4 | Implement automated scheduling system with real-time conflict detection | Use manual backup scheduling system temporarily
R2 | Technical Risk | Downtime or failure of electronic health record (EHR) system | High | High | Critical Risk | 9 | Partner with cloud providers with strong SLAs; set up data backups and failover systems | Activate incident response plan, notify authorities, patch vulnerabilities
R3 | Stakeholder Risk | Resistance from staff to adopt new software or tools | Medium | High | High-priority issue | 6 | Conduct training programs, offer incentives, involve staff early in the transition | If staff resistance persists, introduce champions from key departments to facilitate adoption. Provide additional training and support.
R4 | Financial Risk | Cost overruns due to underestimated implementation or training expenses | Medium | Medium | Mitigation Required | 4 | Establish clear cost estimates, create contingency fund (10–15% of total budget) | Reallocate resources from lower-priority tasks
R5 | Compliance Risk | Failure to meet HIPAA or other health data regulations | Low | High | High-priority issue | 3 | Conduct regular audits, provide data handling workshops for all employees | Engage legal/compliance experts, update policy documentation
R6 | Technical Risk | Unexpected system downtime | Medium | High | Critical Risk | 6 | System monitoring and robust backup systems | In case of a data breach, immediately isolate affected systems and notify IT teams. Conduct root cause analysis and implement emergency fixes.